## Threat & Feasibility Summary
AreaID | TU Unit ID | Fire Threat Class | Feasibility Class | TU Area_ha
TA-3 | TU-3 | Extreme | High | 14
TA-8 | TU-8S | Extreme | High | 9
TA-8 | TU-8N | Extreme | High | 10
TA-9 | TU-9E | Extreme | High | 10
TA-9 | TU-9W | High | High | 9
TA-5 | TU-5 | High | High | 18
TA-1 | TU-1 | High | Moderate | 46
TA-4 | TU-4 | Moderate | Moderate | 34
TA-2 | TU-2 | Moderate | Low | 21
TA-6 | TU-6 | Low | High | 18
TA-7 | TU-7 | Low | High | 14
FireSmart Units
TA_FS100 | TU_FS100_HP | High | Moderate | 5
TA_FS50 | TU_FS50_HP | High | Moderate | 2
TA_FS100 | TU_FS100_EW | Moderate | High | 3
TA_FS100 | TU_FS100_CCW_B | Moderate | Moderate | 3
TA_FS50 | TU_FS50_CCW_B | Moderate | Moderate | 1
TA_FS50 | TU_FS50m_GW | Moderate | Moderate | 1
TA_FS50 | TU_FS50_EW | Low | High | 1
TA_FS100 | TU_FS100_GW | Low | Moderate | 3

## Treatment Areas
GENERAL INFO |  | ADMINISTRATION |  |  |  | STAND ATTRIBUTES | [17 empty] | TREATMENT STRATEGIES |  |  |  |  | TREATMENT/HARVEST DETAILS |  |  |  | Plot Data
Unit Identifier | Area (ha) | Land Ownership/Tenure | Responsibility Area | Existing Tenure Holder | Overlapping Objectives | BEC Zone | BEC Subzone | Slope | Fuel Type (Field Observed) | CMT Present (Y / N) | Forest Health Issues | Overstory Density (trees/ha) | Overstory Composition | Understory Density (trees/ha) | Understory Composition | Standing Dead Percentage | Age Class Code | Crown Base Height Class Overstory (layer 1 trees) | Fuel Strata Gap | Surface Fuel Loading (coverage) | Surface Fuel Loading (Coarse >7cm) | Surface Fuel Description (need to describe our expectation are for this) | Treatment Objective and Strategy Rationale | Overstory Thin? [Reduce Canopy Bulk Density] | Understory Thin? [Reduce Ladder Fuels and Canopy Bulk Density] | Prune? [Raise Canopy Base Height + Reduce Ladder Fuels] | Surface Fuel Reduction? [Reduce Loading/Change Composition] | Broadcast Burn Opportunity? [Reduce fine fuels; ecosystem restoration] | Recommended Treatment Method (Hand, Mechanical, both) | Estimated Volume Present (cubic m/ha) | Operability Concerns (Y/N) | Additional Comments | Proximity Score | Wildfire Threat Score | Wildfire Threat Rating (using the Wildfire Threat Assessment Worksheet WTA Score for Coast and Muntains, 2020)
TU-1 | 46 | SCCF | Sunshine Coast Regional District. | License K3F - Sunshine Coast Community Forest, Crown Land | Water Licenced Work Line: 603208205, Trapline: TR0205T012, FDU: Chapman & CFA, Gray Creek Community Watershed, VLI: 1284 & 1280 | CWH | xm1 | 10 - 20% | C-5 | Y | N/A | 401 - 600 | Conifer w/ Low CBH | 1201 - 1500 | Conifer, moss, herbs, deciduous shrubs | <20% | 4 | < 5m | < 3m | < 10 % |  | Moss, Herbs, Deciduous Shrubs | Interface treatment - important have very low surface fuels and integrate with FireSmart vegetation obejectives when treatment overlaps FireSmart vicinity or 100 m from footprints of homes. Polygon overlap with 2021 SCRP CWRP Treatment Unit #15 and the BCWS Focus Area Tuwanek Fuel Break | Yes, but likely minimal. BA removal <25% expected. | Significant conifer understory stem removal expected. | Prune retained conifers up to 3m. | Will require at minimum <1.0 kg/m2 and < 100 pieces of CWD per hectare. | Unlikely as burning window is very small, forest ecology would not support this type of wildfire with tree retention and likely politically very unsavoury. | The overall area is steep and may have geotechnical issues. Therefore a significant portion is likely manual treatment. | Minimal and likely <30 m3/ha and size classes of conifers less than 22 cm DBH. | Very steep sections with sloughing soils and stability concerns - a geotechnician will need to be involved during FMP development. | None | 32 | 53 | Moderate
TU-2 | 21 | SCCF | Sunshine Coast Regional District | License K3F - Sunshine Coast Community Forest, Crown Land | FDU: Chapman & CFA, VLI: 1284, Trapline: TR0205T012 | CWH | xm1 | 20 - 40% | C-5 | N | N/A | 401 - 600 | Conifer w/ Moderate CBH | < 500 | Conifer, moss, herbs, deciduous shrubs | < 20% | 4 & 5 | 5 - 9 m | 3 - 6m | < 10% |  | Moss, Herbs, Deciduous Shrubs | This unit is situated within community but not immediately adjacent to homes or businesses. The TU would effectively support the reduction in wildfire spread as it approached the Sechelt community. sufficiently outside of protected or high use areas so more opportunities for various treatment activities are available. Polygon overlap with 2021 SCRP CWRP Treatment Unit #17 | An opportunity for signficant overstory thinning and removal can be considered. Anticipated BA removal ~40-60%. | Significant understory should be considered to be removed - appx. 75% of total stems removed. Consideration for leave of some stems for future merchantable timber should be considered. | Pruning at minimum of 2m on conifers should be considered. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Other than cultural burning - broadcast burning is unlikely to be an acceptabel practice this close to community. Although the potential for slash fuel burning in a broadcast setting could be feasible but only under a carefully prepared professional burn plan. | Mechanical is recommended but is dependent on possibility for commercial thinning opportunities. | UNK until field work and an FMP are prepared. | Access is an issue as no road access is available. | None at this time. | 44 | 36 | Low
TU-3 | 14 | SCCF | Sunshine Coast Regional District | License K3F - Sunshine Coast Community Forest, Crown Land | Trapline: TR0205T012, FDU: Chapman & CFA, OGMA: SRY_225_58, Gray Community Watershed, VLI: 1652 | CWH | vm1 | 20 - 40% | C-5 | Y | N/A | 401 - 600 | Conifer w/ Moderate CBH | 801 - 1200 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | < 20% | 4 | 5 - 9m | 3 - 6m | 26 - 50% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This proposed treatment was identified as primarily an ignition reduction unit. The treatment could also reduce potential wildfire spread. | Since this is a roadside treatment for ignition, an overstory removal if not clearcut is likely recommended but dependent on a site visit and FMP preparation. | Significant understory tree removal should be considered | May be unnecessary if overstory trees and understory trees are removed. | A feathered approach to surface fuel reduciton should be considered with very high reduction closest to the road. Broadcast burning in tight strips should be considered. | Yes, limited broadcast burning along the road should be considered. Pile burning maybe a viable alternative. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | UNK until field work and an FMP are prepared. | None. | 45 | 62 | High
TU-4 | 34 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | Water Licensed Works: Multiple, FDU: Chapman & CFA, Trapline: TR0205T012, OGMA: SRY_225_56, SAR: Sitka spruce / salmonberry Very Dry Maritime, SEI Polygons: Multiple, VLI 1280 & 1284 | CWH | xm1 | 10 - 30% | C-4 / C-5 | Y | N/A | 401 - 600 | Conifer w/ Moderate CBH | < 500 | Conifer, moss, herbs, deciduous shrubs | < 20% | 4 & 5 | 5 - 9m | 3 - 6m | < 10% |  | Moss, Herbs, Deciduous Shrubs | Interface treatment and within and overlapping Hidden Grove/Sechelt Heritage Forest Recreation Site - important have very low surface fuels and integrate with FireSmart vegetation objectives when treatment overlaps FireSmart vicinity or 100 m from footprints of homes. Polygon borders with the 2021 SCRP CWRP Treatment Unit #16 and the BCWS Focus Area Sechelt Heritage Forest Polygon. | Yes, but likely minimal. BA removal <25% expected. | Significant conifer understory stem removal expected. | Prune retained conifers up to 3m. | Will require at minimum <1.0 kg/m2 and < 100 pieces of CWD per hectare. | Unlikely as burning window is very small, forest ecology would not support this type of wildfire with tree retention and likely politically very unsavoury. | The area is favourable for mechanical operations. | Minimal and likely <30 m3/ha and size classes of conifers less than 22 cm DBH. | Minimal - although skid trail and road building may not politically acceptable. | The area overlaps high recreation use and high value forests to the public. Significant care must be taken to build trust and understanding with the community before treatment activities commence. Furthermore, Wildfire risk reduction treatments within the Sechelt Heritage Forest (REC 6206) require S.16 authorization for industrial activity within a S.56 established site or trail under the Forest Recreation Regulation. Here is a link where the application form and guidelines document are located: https://www2.gov.bc.ca/gov/content/sports-culture/recreation/camping-hiking/sites-trails/program/authorizations. think it will be prudent to complete an on-site review with Mike Davidson as part of the prescription development. | 32 | 25 | Low
TU-5 | 18 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, VLI: 1353 & 1324 | CWH | xm1 | 0 - 20% | C-3 | N | N/A | 601 - 900 | Conifer w/ Moderate CBH | < 500 | Conifer, Lichen, Conifer Shhrubs | <20% | 2 | 5 - 9m | 3 - 6m | < 10% |  | Lichen, Conifer Shrubs | This unit overlaps an SCRD CWPP proposed treatment and was identified as both a unit to assist in reducing wildfire risk to the airport but also as an example of fuel management forest activities. Polygon overlaps with the 2021 SCRP CWRP Treatment Unit #1 and the BCWS Focus Area Sechelt Airport Polygon. | Some overstory will be recommended, likely <40% BA removal. | Significant understory removal will be recommended (>80% stem density removal) | Pruning at minimum of 2m on conifers should be considered. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | If significant overstory and understory are removed then a broadcast burn should be considered but this needs to be determined at the FMP development stage. | Mechanical or manual but this will be determined in consultation with the SCCF. | Low volume (~<50m3/ha). | None. |  | 45 | 56 | Moderate
TU-6 | 18 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T012 & TR0205T015, VLI: 1284 | CWH | dm | 10 - 30% | D-1/2 / C-5 | Y | Douglas Fir Beetle | 601 - 900 | Conifer w/ Moderate CBH | 501 - 800 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | <20% | 2 | 5 - 9m | 3 - 6m | 10 -25% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This unit supports landscape level reduction of wildfire risk. It additionally supports an important electrical RoW line adjacent to the unit. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal. | Moderate pruning of Hw and Cw species of various sizes. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  |  | - | -
TU-7 | 14 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T012 & TR0205T015, VLI: 1284 | CWH | dm | 10 - 50% | C-5 | Y | N/A | 401 - 600 | Conifer w/ Moderate CBH | < 500 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | <20% | 3 | 5 - 9m | 3 - 6m | < 10% |  | Moss, Herbs, Deciduous Shrubs | This unit supports landscape level reduction of wildfire risk. It additionally supports an important electrical RoW line adjacent to the unit. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal. | Moderate pruning of Hw and Cw species of various sizes. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  |  | - | -
TU-8N | 15 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T015, Forest Cover Reserves: 113602, OGMA: SRY_225_122, VLI: 1353 | CWH | dm | 10 - 30% | C-5 | N | N/A | <400 | Conifer w/ Moderate CBH | 1201 - 1500 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | 21 - 50 % | 8 | 5 - 9 m | 3 - 6 m | 10 -25% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This unit supports landscape level reduction of wildfire risk as well as reduction in ignition potential. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal or higher. | Moderate pruning of Hw and Cw species of various sizes where retained stems exist. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  | 43 | 63 | High
TU-8S | 15 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T015, Forest Cover Reserves: 113602, OGMA: SRY_225_122, VLI: 1353 | CWH | dm | 10 - 30% | C-3 | N | N/A | <400 | Conifer w/ Moderate CBH | 1201 - 1500 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | 21 - 50 % | 8 | 5 - 9 m | 3 - 6 m | 10 -25% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This unit supports landscape level reduction of wildfire risk as well as reduction in ignition potential. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal or higher. | Moderate pruning of Hw and Cw species of various sizes where retained stems exist. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  | 45 | 63 | High
TU-9E | 10 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T015, Forest Cover Reserves: 80983 & 1295051, OGMA: SRY_225_122, VLI: 1353, Sensitive Ecosystem Inventory: Multiple, SAR: Sitka spruce / salmonberry Dry (18218155), VLI: 1353 | CWH | dm / xm1 | 10 - 20% | C-5 | N | N/A | 801 - 1200 | Conifer w/ Moderate CBH | 801 - 1200 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | < 20 % | 2 & 6 | 5 - 9 m | 3 - 6 m | 10 -25% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This unit supports landscape level reduction of wildfire risk as well as reduction in ignition potential. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal or higher. | Moderate pruning of Hw and Cw species of various sizes where retained stems exist. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  | 43 | 58 | High
TU-9W | 9 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | FDU: Chapman & CFA, Trapline: TR0205T015, Forest Cover Reserves: 80983 & 1295051, OGMA: SRY_225_122, VLI: 1353, Sensitive Ecosystem Inventory: Multiple, SAR: Sitka spruce / salmonberry Dry (18218155), VLI: 1353 | CWH | dm / xm1 | 10 -20 % | C-3 | N | N/A | 501 - 800 | Conifer w/ Moderate CBH | 501 - 800 | Conifer, Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | 21 - 50 % | 2 & 6 | 5 - 9 m | 3 - 6 m | 10 -25% |  | Dead fines (Leaves, Needles or fine branch material) fuel (<1cm) | This unit supports landscape level reduction of wildfire risk as well as reduction in ignition potential. | This is recommended due to the high likelihood of merchantable timber in the TU. | Yes, significant removal should occur, likely between 50 and 70% stem density removal or higher. | Moderate pruning of Hw and Cw species of various sizes where retained stems exist. | Surface fuel reduction will be important and should be tailored and depend on other fuel reduction measures (thinning and pruning). | Broadcast burning of slash in areas of minimal tree retention may be a possibility given support for cultural burning and BCWS or other local firefighters. A burn plan should be written by a professional. | Mechanical is recommended. | UNK until field work and an FMP are prepared. | None. |  | 43 | 44 | Moderate
TU_FS100_CCW_B | 3 | Private | Sunshine Coast Regional District | Private | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (water intake) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 100 is to implement FireSmart Critical infrastructure practices for a 100 m buffer around the Commuications tower. Vegetation management that should be implemented is clearing all conifer vegetation within Extended and Intermediate Zone as well as clear any and all vegetation within the fenced area of the Communications tower. Conifer Vegetation can be pruned to 3 m and all dead / dying trees should be removed. | [9 empty] | - | - | N/A
TU_FS50_CCW_B | 1 | Private | Sunshine Coast Regional District | Private | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (water intake) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 50 is to implement FireSmart Critical infrastructure practices for a 50 m buffer around the Commuications tower. Vegetation management that should be implemented is clearing all conifer vegetation within the buffer area as well as clear any and all vegetation within the fenced area of the Communications tower. | [9 empty] | - | - | N/A
TU_FS100_GW | 3 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (water intake) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 100 is to implement FireSmart Critical infrastructure practices for a 100 m buffer around the Water Intake. Vegetation management that should be implemented is clearing all conifer vegetation within Extended and Intermediate Zone as well as clear any and all vegetation within the fenced area of the Water Intake. Conifer Vegetation can be pruned to 3 m and all dead / dying trees should be removed. | [9 empty] | - | - | N/A
TU_FS50m_GW | 1 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (water intake) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 50 is to implement FireSmart Critical infrastructure practices for a 50 m buffer around the Water Intake. Vegetation management that should be implemented is clearing all conifer vegetation within the buffer area as well as clear any and all vegetation within the fenced area of the water intake. | [9 empty] | - | - | N/A
TU_FS100_EW | 3 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (comms tower) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 100 is to implement FireSmart Critical infrastructure practices for a 100 m buffer around the Water Intake. Vegetation management that should be implemented is clearing all conifer vegetation within Extended and Intermediate Zone as well as clear any and all vegetation within the fenced area of the Water Intake. Conifer Vegetation can be pruned to 3 m and all dead / dying trees should be removed. | [9 empty] | - | - | N/A
TU_FS50_EW | 1 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (comms tower) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 50 is to implement FireSmart Critical infrastructure practices for a 50 m buffer around the Commuications tower. Vegetation management that should be implemented is clearing all conifer vegetation within the buffer area as well as clear any and all vegetation within the fenced area of the Communications tower. | [9 empty] | - | - | N/A
TU_FS100_HP | 2 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (comms tower) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 100 is to implement FireSmart Critical infrastructure practices for a 100 m buffer around the Commuications tower. Vegetation management that should be implemented is clearing all conifer vegetation within Extended and Intermediate Zone as well as clear any and all vegetation within the fenced area of the Communications tower. Conifer Vegetation can be pruned to 3 m and all dead / dying trees should be removed. | [9 empty] | - | - | N/A
TU_FS50_HP | 5 | SCCF | Sunshine Coast Regional District | License K3F - Sunishine Coast Community Forest | - | FireSmart Treatment units are based on proximity of fuels/ vegetation to Critical infrastrucutre (comms tower) Stand attributes not included in Critical Infrastrucutre Assessments | [16 empty] | Treatment objective for FS 50 is to implement FireSmart Critical infrastructure practices for a 50 m buffer around the Commuications tower. Vegetation management that should be implemented is clearing all conifer vegetation within the buffer area as well as clear any and all vegetation within the fenced area of the Communications tower. | [9 empty] | - | - | N/A